## Running Plan
Mystery Show ¦ 1 - 31 May 2019 | Template document created by Isabel Dixon (@isabel_dixon) | £600 (inclusive of VAT)
Activity | Details | Dates | Cost - Gross | Cost - Net | Status
Print
Posters - A3 | 50 130gsm (Solopress) - general distribution | 2019-04-01 | 27.48 | 22.9
Flyers - A5 | 1000 200gsm (Solopress) - general distribution | 2019-04-01 | 44 | 44
Print Advertising
Quarter page ad in local paper | Specs: 90mm x 130mm, no bleed | Running 1 week from 1st April | 120 | 100
Online Advertising
OffWestEnd.com e-shot | To supply: show copy (150 words), image and booking link | 29th April | 72 | 60
Social Media
Facebook Advertising | Trailer boosted post - 1 week, targeted to London new writing audience | w/c 8th April | 40 | 33.3333
Facebook Advertising | Trailer boosted post - 1 week, targeted to relevant interest groups | w/c 8th April | 40 | 33.3333
Facebook Advertising | Best of' reviews / content posts x 3 | Throughout run tbc | 60 | 50
Direct Marketing
Email contact | Emailing relevant charities, interest groups, etc | w/c 8th April | 0 | 0
Distribution
Postering & Flyering | 3 hours postering/flyering cafes/shops in local area - Divided up amongst company | W/C 15th April | 0 | 0
Street Team | 4 hours postering/flyering cafes/shops in local area - Divided up amongst company | W/C 22nd April | 0 | 0
Street Team | 4 hours exit flyering shows and other relevant cross promo - paid freelancer at £10/hour | Throughout April | 48 | 40
In House Promotion (Venue Support)
Social Media | Short form/content based via theatre's channels | on sale - end of run | FREE | FREE
FOH displays | Digital screens, postering - content and maintenance | on sale - end of run | FREE | FREE
Promotional support via networks | Promo swaps with relevant partners, etc | on sale - end of run | FREE | FREE
E-newsletters | Inclusion on venue's mail outs | on sale - end of run | FREE | FREE
Solus Email | Direct email to previous bookers of relevant shows | W/C 29th April | FREE | FREE
Fees
Designer | Flyers and poster design - created by company members | Pre - on sale | 0 | 0
Photography | Production photography - discount negotiated | Tech day (date tbc) | 120 | 100
Photography | Rehearsal shots - taken by company members | April tbc | 0 | 0
Contingency
TBC | Held back for emergency use |  | 50 | 41.6667
|  | TOTAL | 621.48 | 525.2333

## Week By Week
Show Name ¦ Show Dates | Italics = not yet fully scheduled to exact day
Week Commencing:
Monday
Tuesday
Wednesday
Thursday
Friday
Saturday
Sunday
Week Commencing:
Monday
Tuesday
Wednesday
Thursday
Friday
Saturday
Sunday
Week Commencing:
Monday
Tuesday
Wednesday
Thursday
Friday
Saturday
Sunday
Week Commencing:
Monday
Tuesday
Wednesday
Thursday
Friday
Saturday
Sunday
Week Commencing:
Monday
Tuesday
Wednesday
Thursday
Friday
Saturday
Sunday
Week Commencing:
Monday
Tuesday
Wednesday
Thursday
Friday
Saturday
Sunday
Week Commencing:
Monday
Tuesday
Wednesday
Thursday
Friday
Saturday
Sunday